## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Project setup | 0.25 | 2024-01-26 | Finished setting up Github repository and Unity project.
Research | 0.25 | 2024-01-26 | Researched about perfect maze algorithms and deciding which one I will implement. I used the wikipedia page provided on the assessment description for this.
Theory familiarization | 0.45 | 2024-01-26 | Read about the Randomized Kruskal's Algorithm and understanding how to approach its implementation.
Cell instantiation | 1.75 | 2024-01-26 | Implemented a script that instantiates a n x m grid of cell game objects, and created very basic prefabs for the cells and walls of the maze.
Wall instantiation | 0.5 | 2024-01-26 | Implemented the generation of the wall game objects at the edges of each cell game object.
Kruskal's algorithm implementation | 1 | 2024-01-26 | Implemented the randomized Kruskal's algorithm! Performance was an issue for a maze that is 250 by 250, but it works. Used http://weblog.jamisbuck.org/2011/1/3/maze-generation-kruskal-s-algorithm for reference.
Camera setup | 0.5 | 2024-01-26 | Wrote some code to move the camera so that it shows on the center of the screen, and to add the top, bottom, left ad right borders.
Sequential maze visualization | 0.5 | 2024-01-27 | Implemented a coroutine to sequentially disable the wall game objects to generate the maze.
UI setup and game manager setup | 2 | 2024-01-27 | Implemented the UI and game management so that user input values are not destroyed on load.
Camera tuning | 0.5 | 2024-01-27 | Fixed a bug with the camera size. It was not showing the maze properly for very wide mazes. Used https://discussions.unity.com/t/adjust-orthographic-camera-to-fit-object/130223 for reference.
Performance optimization | 1.5 | 2024-01-28 | Fixed performance of large mazes by combining meshes of the border, cells and walls that won't be removed.
Scene persistance | 2 | 2024-01-28 | Implemented scene persistence between the maze and the main menu, and created the methods to reset and restart the maze.
Camera final tuning | 1.5 | 2024-01-28 | Fixed a bug with how the mazes were displayed. Now the camera's orthographic size is dynamically adjusted.
Performance optimization | 1.5 | 2024-01-29 | Tried some different things to optimize the performance (i.e. tried to used sprites instead of 3D game objects), but had no luck. Kept 3D objects with mesh combining for simplicity.
Camera zooming and panning | 0.5 | 2024-01-29 | Implemented zoom and panning of the camera to make sure user can see the entire maze (works with mouse only). | x
Game mode | 2.75 | 2024-01-29 | Created a nice game simulation in which a player can navigate the maze. | x
Documentation | 1.5 | 2024-01-29 | Added comments to the scripts and wrote a README.
Documentation | 0.5 | 2024-01-30 | Filled in the hour log and submitted.
Total amount of hours | 16.2